## Vidyalu
VIDYALU- A LEARNING PLATFORM
STACK - Angular / Python Django REST API / MySQL
Team
| Business Team | Designer Team | Front End Team | Backend Team
| Gautam C. | Quaisar | Gujan | Suman M. , Safakat
WBS
Milestone no | Module | Total Estimated [ Working Days] | Date of delivery | Development Status | Delivery Status | Payment Receive Status
1 | Project Report Analysis | 10 Days | 19-05-2021 | Completed | delivered | Yes
2 | URS and Wireframes | 20 Days | 21-06-2021 | Completed | delivered | Yes
3 | UI Designs(Angular) and Database Designs | 20 Days | 15-07-2021 | Completed | delivered | Yes
4 | Dynamic Pages for Student,Faculty,Counsellor,Admin | 20 Days | 30-07-2021 | Completed | delivered | Yes
5 | All users can able to connect to database and redirect to respective dashboard | 20 Days | 15-08-2021 | Completed | delivered | Yes
6 | All users can able to update their profiels, verification link Expires time limit, Ability to seach teacher , counsellor zip code wise,course wise | 20 Days | 25-08-2021 | Completed | Delivered | Yes
7 | Dashboard for Faculty/Instructor/Teacher with complete functionality | 20 Days | 15-09-2021 | Completed | Delivered | Not claimed
8 | Dashboard for Counsellor with complete functionality | 15 Days | 30-09-2021 | In progress | No | Not claimed
9 | Dashboard for Admin with complete functionality with End to End functionality of project with Testing reports | 25 Days | 15-10-2021 | TO DO |  | Not claimed
10 | Review reports ,Audit Reports , Updates recommendation (if any) | 10 Days | 30-10-2021 | TO DO | No | Not claimed
| TOTAL ESTIMATED TIMEFRAME | 185 business days

## Omnireels-A replica of NetFlix
Omnireels – A replica of NetFlix
STACK - Native / Node JS /Mongo DB
Team
| Business Team | Designer Team | Front End Team-APP Developent | Backend Team
| Daljit/Rahul | Sudhangshu | Ayan - Native /IOS | Saddam A. / Rohit Deshmukh
Mrinmoy- Native/Android
WBS
Milestone No | Module | Time estimate [Working days] | Date of delivery | Development Status | Delivery Status | Payment Receive Status
1 | Project report / Wireframe design | 15 business days | 09-07-2021 | Completed | Delivered | -
2 | UI Screen Design (XD) | 10 business days | 19-07-2021 | Completed | Delivered | -
3 | Database structure and Admin section development | 30 business days | 16-08-2021 | In progress | In progress | -
4 | Web services for application | 30 business days | 16-09-2021 | TO DO | TO DO | -
5 | User management and subscription, ACH implementation, packages distribution etc | 30 business days | 16-10-2021 | TO DO | TO DO | -
6 | Streaming and storage server implementation, app feature like play video, resume, language, subtitle and all functionality implementation. | 30 business days | 16-11-2021 | TO DO | TO DO | -
7 | Testing and debugging and go live. | 25 business Days | 2021-10-12 | TO DO | TO DO | -
8 | Updates and final report submission, Audit Report | 15 business days | 25-12-2021 | TO DO | TO DO | -
| TOTAL ESTIMATED TIMEFRAME | 185 business days

## Atacos Cab Booking App
ATACOS cab booking app
STACK - React Native/Laravel/My-Sql
Team
| Business Team | Designer Team | Front End Team | Backend Team
| Rahul | Arijit | Arnab | Suman Sadukhan
WBS
Milestone no | Module | Time Estimate [Working Days] | Date of delivery | Development Status | Delivery Status | Payment Receive Status
1 | Project Report Developement , Team Allocation | 2 days | 2021-02-08 | Done | Done | -
2 | Wireframe UI design | 5 Days | 2021-07-08 | Done
3 | User Section (App for Android and iOS) | 45 Days | 30-09-2021 | In Progress
4 | Drivers Section (App for Android and iOS) | 45 Days | 20-11-2021 | To Do
5 | Admin Login (web based) | 45 Days | 2022-05-01 | In Progress
6 | Quality Testing , Audit Reports | 8 Days | 15-01-2022 | TO Do
| Total Estimated Time Frame | 150 Working Days

## 4Today App
4Today App
STACK - React Native/Laravel/My-Sql
Team
| Business Team | Designer Team | Front End Team | Backend Team
| Rahul | Ayan | Shubhom | Vijay Kumar
WBS
Milestone no | Module | Time Estimate[Working Days] | Date of delivery | Development Status | Delivery Status | Payment Receive Status
1 | Project Report Developement , Team Allocation | 2 Days | 28-07-2021 | Done | Done | -
2 | Wireframe UI design | 8 Days | 2021-08-08 | Done
3 | React Native App design | 20 Days | 30-08-2021 | In Progress
4 | Admin Web Development , API development | 15 Days | 20-09-2021 | In Progress
5 | Quality Testing ,Audit Report | 5 Days | 30-09-2021 | To Do
| Total Estimated Time Frame | 50 Working Days

## Recruiting Agency App
Recruiting Agency App
STACK - React Native/Laravel/My-Sql
Team
| Business Team | Designer Team | Front End Team | Backend Team
| Rahul | Arijit | Shubhom | Subhashish
WBS
Milestone no | Module | Time Estimation [Working Days] | Date of delivery | Development Status | Delivery Status | Payment Receive Status
1 | Project Report Developement , Team Allocation | 1 Day | 28-07-2021 | Done | Done | -
2 | Wireframe UI design | 2 Days | 2021-01-08 | Done | Done
3 | App UI Developement | 4 Days | 2021-08-08 | Done | Done
4 | Admin Web, API developement | 2 Days | 2021-12-08 | Done | Done
5 | Quality Testing ,Report | 1 Day | 16-08-2021 | Done | Done
| Total Estimated Time Frame | 10 working days

## Adamsea
Adam Sea - Marketplace for boats
STACK - React Native/MERN
Team
| Business Team | Designer Team | Front End Team | Backend Team
| Pradipta | - | React Native -Ritoja, MERN - Rohit | Rohit
WBS
Milestone no | Module | Time Estimate [Working Days] | Date of delivery | Development Status | Delivery Status | Payment Receive Status
1 | Bug Fixes , Global Search ,Search Engine | 15 Days | 15-09-2021 | In Progress | In progress | yes
2 | Rent Module , Chat Application | 15 Days | 2021-06-10 | in Progress | In progress | -
3 | Admin Section ,Mobile App,Mobile Admin Mgt. | 15 Days | 2021-03-11 | To Do
4 | Microservices, Testing,Updates if any | 15 Days | 25-11-2021 | To Do
| Total Estimated Time Frame | 60 Working Days

## CRM
CRM - For Design Firm
TECH STACK - HTML-5 Javascript /Laravel / MySQL
Team
| Business Team | Designer Team | Front End Team | Backend Team
| Ratnesh | Sudhangshu | Quaisar | Shouvik
WBS
Milestone no | Module | Total Estimated [ Working Days] | Date of delivery | Development Status | Delivery Status | Payment Receive Status
1 | Data mapping / BL Design /UI design/Database Development | 17 Days | 17-09-2021 | in progress | - | -
2 | URS and Wireframes | 20 Days | 2021-12-10 | In progress | - | -
3 | Employee Module | 30 Days | 19-11-2021 | To DO | - | -
| TOTAL ESTIMATED TIMEFRAME | 200 working days

## Transapp-A messaging App
TRANSAPP- A messaging app
TECH STACK -React Native - MEAN Stack
Team
| Business Team | Designer Team | Front End Team | Backend Team
Ratnesh
WBS
Milestone no | Module | Total Estimated [ Working Days] | Date of delivery | Development Status | Delivery Status | Payment Receive Status
1 | UI Design/DB Design | 9 Days | 19-10-2021 | in progress | - | -
2 | Admin developemnt/API Development | 17 Days | 2021-12-11 | To do
3 | App deevlopement | 30 days | 27-12-2021 | To do | - | -
4 | Testing /Site configuring | 4 Days | 31-12-2021 | To DO | - | -
TOTAL ESTIMATED TIMEFRAME
| Module | Cost estimate [USD]
| App design | USD 2,200
| DB design | USD 2,200
| Application development | USD 1,600
| Admin development | USD 1,000
| Testing | USD 300
| Site configuration & Hosting | USD 300
| TIME ESTIMATE | USD 7600